## Sheet1
Name | Table | Tasks | Schedule Date | Start Date | End Date | Process | Members | Discription
PIJAMA BE | User | Create | 0.5
|  | Update | 0.5
|  | DELETE | 0.5
|  | GET ALL | 0.5 | 19/02/2023 | 19/02/2024 | 100% | ALL
|  | GET BY ID | 0.5 | 19/02/2023 | 19/02/2024 | 100% | ALL
| User Authentication | Login
|  | Register | 0.5 | 19/02/2023 | 19/02/2024 | 50% | ALL | Thiếu phần json token
ForgotPassword
| Product | CREATE
UPDATE
DELETE
GET ALL
GET BY ID
GET BY CATEGORY ID
| Order | CREATE
UPDATE
DELETE
GET ALL
GET BY ID
GET BY USER ID
| Cart | List product in cart